## I1
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 2. User Account | 2.2 | Modify Account Information | Implement GUI Requirements | 2020-02-23 | 2020-02-24 | 100% | Guanggeng
2 | 2. User Account | 2.2 | Modify Account Information | Implement Core Functionality | 2020-02-23 | 2020-02-24 | 100% | Claire
3 | 2. User Account | 2.2 | Modify Account Information | Implement Entitlement Enforcement | 2020-02-23 | 2020-02-24 | 100% | Guanggeng
4 | 2. User Account | 2.2 | Modify Account Information | Implement Field Validation Enforcement | 2020-02-23 | 2020-02-24 | 100% | Claire
5 | 2. User Account | 2.2 | Modify Account Information | Develop Test Cases For Modify Account Information functionality | 2020-02-23 | 2020-02-24 | 100% | Guanggeng
6 | 3. Donation | 3.1 | Create Donation List | Implement API | 2020-02-28 | 2020-03-05 | 100% | Danni
7 | 3. Donation | 3.1 | Create Donation List | Implement GUI Requirements | 2020-02-28 | 2020-03-05 | 100% | Guanggeng
8 | 3. Donation | 3.1 | Create Donation List | Develop Test Cases for Create Donation List functionality | 2020-02-28 | 2020-03-05 | 100% | Claire
9 | 3. Donation | 3.2 | Donation in honor of | Implement GUI Requirements | 2020-02-28 | 2020-03-05 | 100% | Daniel
10 | 3. Donation | 3.2 | Donation in honor of | Implement Core Functionality | 2020-02-28 | 2020-03-05 | 100% | Daniel
11 | 3. Donation | 3.2 | Donation in honor of | Develop Test Cases for Donation in Honor of functionality | 2020-02-28 | 2020-03-05 | 100% | Daniel

## I2
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 3. Donation | 3.3 | Get Shipping information | Implement GUI Requirements | 2020-03-21 |  | 0% | Claire
2 | 3. Donation | 3.3 | Get Shipping information | Implement Core Functionality | 2020-03-21 |  | 0% | Guanggeng
3 | 3. Donation | 3.3 | Get Shipping information | Implement Internal Entitlements | 2020-03-21 |  | 0% | Claire
4 | 3. Donation | 3.4 | Check donation status | Implement GUI Requirements | 2020-03-21 |  | 0% | Guanggeng
5 | 3. Donation | 3.4 | Check donation status | Implement Core Functionality | 2020-03-21 |  | 0% | Guanggeng
6 | 3. Donation | 3.4 | Check donation status | Implement API | 2020-03-21 |  | 0% | Danni
7 | 3. Donation | 3.5 | View final estimated value | Implement GUI Requirements | 2020-03-21 |  | 0% | Daniel
8 | 3. Donation | 3.5 | View final estimated value | Implement Core Functionality | 2020-03-21 |  | 0% | Daniel
9 | 3. Donation | 3.5 | View final estimated value | Implement Entitlement Enforcement | 2020-03-21 |  | 0% | Daniel

## I3
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 4. Help Desk | 4.1 | Leave message |  |  |  | 0%
2 | 4. Help Desk | 4.1 | Leave message |  |  |  | 0%
3 | 4. Help Desk | 4.1 | Leave message |  |  |  | 0%
4 | 4. Help Desk | 4.2 | Contact information |  |  |  | 0%
5 | 4. Help Desk | 4.2 | Contact information |  |  |  | 0%
6 | 4. Help Desk | 4.2 | Contact information |  |  |  | 0%
7 | 5. Administrator Account | 5.1 | Administrator Account Sign in |  |  |  | 0%
8 | 5. Administrator Account | 5.1 | Administrator Account Sign in |  |  |  | 0%
9 | 5. Administrator Account | 5.1 | Administrator Account Sign in |  |  |  | 0%

## I4
Task # | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | 5. Administrator Account | 5.2 | Modify Administrator Account |  |  |  | 0%
2 | 5. Administrator Account | 5.2 | Modify Administrator Account |  |  |  | 0%
3 | 5. Administrator Account | 5.2 | Modify Administrator Account |  |  |  | 0%
4 | 6. Validation and Evaluation | 6.1 | Verify Donation Items |  |  |  | 0%
5 | 6. Validation and Evaluation | 6.1 | Verify Donation Items |  |  |  | 0%
6 | 6. Validation and Evaluation | 6.1 | Verify Donation Items |  |  |  | 0%
7 | 6. Validation and Evaluation | 6.1 | Generate Donation Value Estimate |  |  |  | 0%
8 | 6. Validation and Evaluation | 6.1 | Generate Donation Value Estimate |  |  |  | 0%
9 | 6. Validation and Evaluation | 6.1 | Generate Donation Value Estimate |  |  |  | 0%