## Road Map l1
Bulletin
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 03/6/20 | Iteration 2 - 04/03/20 | Iteration 3 - 04/24/20 | Iteration 4 - 05/15/20
Module 1 - Home | 01.01 Donation Instruction | 3
| 01.02 Ogranization Description | 3
| 01.03 Activities Board | 3 |  |  |  |  | features completed last semester
Module 2 - User Account | 02.01 User Account Sign in/up | 3
| 02.02 Modify User Account Information | 3 | X
Module 3 - Donation | 03.01 Create Donation List | 3 | X
| 03.02 Donation In Honor Of | 3 | X
| 03.03 Get Shipping Information | 3 |  | X
| 03.04 Check Donation Status | 3 |  | X
| 03.05 View Final Estimated Value | 3 |  | X
Module 4 - Help Desk | 04.01 Leave Message | 3 |  |  | X
| 04.02 Contact Information | 3 |  |  | X
Module 5 - Administrator Account | 05.01 Administrator Account Sign In | 3 |  |  | X
| 05.02 Modify Administrator Account | 3 |  |  |  | X
Module 6 - Validation and Evaluation | 06.01 Verify Donation Items | 3 |  |  |  | X
| 06.02 Add/Delete Student | 3 |  |  |  | X
|  | Velocity : | 9 | 9 | 9 | 9

## Road Map l2
Bulletin
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points | Iteration 1 - 03/6/20 | Iteration 2 - 04/03/20 | Iteration 3 - 04/24/20 | Iteration 4 - 05/15/20
Module 1 - Home | 01.01 Donation Instruction | 3
| 01.02 Ogranization Description | 3
| 01.03 Activities Board | 3
Module 2 - User Account | 02.01 User Account Sign in/up | 3 |  |  |  |  | features completed last semester
| 02.02 Modify User Account Information | 3 | X
Module 3 - Donation | 03.01 Create Donation List | 3 | X
| 03.02 Donation In Honor Of | 3 | X
| 03.03 Get Shipping Information | 3 |  | X
| 03.04 Check Donation Status | 3 |  | X
| 03.05 View Final Estimated Value | 3 |  | X
Module 4 - Help Desk | 04.01 Leave Message | 3 |  |  | X
| 04.02 Contact Information | 3 |  |  | X
Module 5 - Administrator Account | 05.01 Administrator Account Sign In | 3 |  |  | X
| 05.02 Modify Administrator Account | 3 |  |  |  | X
Module 6 - Validation and Evaluation | 06.01 Verify Donation Items | 3 |  |  |  | X
| 06.02 Add/Delete Student | 3 |  |  |  | X
|  | Velocity : | 9 | 9 | 9 | 9

## Roles Traceability
User Roles vs. Features Matrix
User Roles | 01. Home |  |  | 02. User Account |  | 03. Donation |  |  |  |  | 04. Help Desk |  | 05. Administrator Account |  | 06. Validation and Evaluation
| Donation Instruction | Organization Descirption | Activites Board | User Account Sign in/up | Modify User Account Information | Create Donation list | Donation In Honor Of | Get Shipping Information | Check Donation Status | View Final Estimated Value | Leave Message | Contact Information | Administrator Account Sign In | Modify Administrator Account | Verify Donation items | Generate Donation Value Estimate
| 1.01 | 1.02 | 1.03 | 2.01 | 2.02 | 3.01 | 3.02 | 3.03 | 3.04 | 3.05 | 4.01 | 4.02 | 5.01 | 5.02 | 6.01 | 6.02
Distribution Manager |  |  | X |  |  |  | X | X | X |  |  | X
Fleet team Manager | [7 empty] | X | X
Data Analyst |  |  |  |  | X | X |  |  |  | X |  |  |  | X
Financial Manager | [10 empty] | X | X
Administrator | X | X |  | X | X | [5 empty] | X |  | X | X | X | X
User Support | [5 empty] | X | X
Account Manager |  |  |  | X | X | [8 empty] | X

## Role Descriptions
USER ROLES
Distribution Manager
These users only have access to the list of donated items, as well as list of non-profit organizations requesting those products. They are responsible for coordinating what goods go where.
Fleet team Manager
These are users that are given the direction of where each donated good goes, and are responsible for packaging and preparing for shipment.
Data Analyst
These are users that have access to all end-user data in order to provide distribution managers, and fleet team managers the necessary information for them to do the back end work for our business solution.
Financial Manager
These are users that only have access to the help desk module, where end users are able to find the financial teams contact information.
Administrator
These users are the core stakeholders who lay the foundation like the lead developer, product owner, lead business analyst, product manager and lead QA. They have all the privileges to edit, update or delete anything in the database.
User Support
These are users that are responsible for assisting in trouble shooting and serving as the first line of defense for end user issues
Account Manager
These are users that are responsible for assisting end users in creating their accounts. They will be able to help manage accounts going forward as well.