## User Story Backlog
User Stories
DonationPlace Solution
Module | ID | Title | As a/an | I want to… | so that I can… | Iterations | Story Points | Story Contraints
1.Home | 1.1 | Donation Instruction | User, Administrator | View instructions on how to donate. | Process items to be donated. |  | 3 | Users and Administrators should be able to View instructions on how to donate Within the main home page of the application
| 1.2 | Organization Description | User, Non Profit Organization, Administrator | View the Organization Description. | See what DonationPlace Solutions stands for as a Company |  | 3 | Users, Administrators, and Non Profit Organizations can view the description text field, but only Administrators and Non Profit Organizations should be able to edit it.
| 1.3 | Activities Board | User, Distribution Manager | View the Activities Board. | Participate in activities. |  | 3 | User, Distribution Manager will view the Activities Board when they log into the application as administrators, or regular users. Ensure that they have these privileges.
2.User Account | 2.1 | User Account Sign in/up | User, Accountant, Administrator | Have an option to register. | Access my account. |  | 3 | Users, Accountants, and Administrators access the registration page upon launching the application.
| 2.2 | Modify Account Information | User, Accountant, Administrator, Data Analyst | Have an option to change account information. | Modify details of my account. | I1 | 3 | Registered users have the ability to change their login credentials upon launching the application and entering the menu option for it, regardless of being administrators or not.
3.Donation | 3.1 | Create Donation list | User, Non Profit Organization, User Support, Data Analyst | Have an option to create a list of donated items. | Insert items. | I1 | 3 | The application allows for registered users to add items to a list which integrates with the Firebase database.
| 3.2 | Donation In Honor Of | User, User Support, Distribution Manager | Have option to donate in honor of someone. | Modify donation and encourage participation | I1 | 3 | The donation has an option to be in honor of someone else, and enter the name of the person they are donating in honor of.
| 3.3 | Get Shipping Information | User, Delivery System, Fleet Team Manager, Distribution Manager | Request shipping information. | View address of item recipients. | I2 | 3 | Users should be able to enter their shipping information in their account, and the , Delivery Systems, Fleet Team Managers, Distribution Manager should be able to view it in the Firebase Database
| 3.4 | Check Donation Status | Users, Government Agencies, Financial Manager | View donation status. | Check status of donation. | I2 | 3 | The Users should be able to view the status of their donation until its processing, and the Delivery System, Fleet Team Manager, Distribution Manager should be able to view and edit the status on their external system.
| 3.5 | View Final Estimated Value | Users, Government Agencies, Financial Manager | View value of return estimation. | Review the estimate and add it to my tax return. | I2 | 3 | Users should be able to see the text field for their estimated tax returns, and the administrative users should be able to edit and set these values.
4.Help Desk | 4.1 | Leave Message | Users, Government Agencies, User Support, Administrator | Leave the Help Desk a message. | Recieve technical support based on my inquiry. | I3 | 3 | Users should be able to leave a message for the IT support team which in turn generates an Email with Timestamp to the IT Help Desk team and automatically generates a ticket in their Zendesk ticketing system.
| 4.2 | Contact Information | Users, Government Agencies, Non Profit Organizations, Delivery Systems, Financial Manager, Distribution Manager | View Contact Information of the Help Desk | Verify I am contacting the Help Desk. | I3 | 3 | All users should be able to view Contact Information of the Help Desk in order to call and create an IT ticket for the global 24 hour help desk.
5. Administrator Account | 5.1 | Administrator Account Sign In | Administrator | Have an option for an Administrator login. | Perform duties on application with elevated privileges. | I3 | 3 | Administrators should be recognized once they log into the application and be part of a special group policy which allows them to have elevated privileges.
| 5.2 | Modify Administrator Account | Administrator, Accountant, Data Analyst | Have option to modify Administrator account. | Modify administrator account information. | I4 | 3 | Administrators alone should be able to log into their account and use a text form to modify their account. In testing ensure that non administrator users can modify the administrator accounts.
6.Validation and Evaluation | 6.1 | Verify Donation Items | Administrator | Verify items set for donation are correct. | Send items to non profit organizations and have the IRS process a return. | I4 | 3 | Administrators can modify the text form which corresponds to users donations in order to ensure they are correct.
| 6.2 | Generate Donation Value Estimate | Administrator | Estimate the value of items donated. | Estimate the amount of money that will be added to the tax return. | I4 | 3 | Administrators can modify the text form which corresponds to users donations in order to ensure they are correct, and can assess the value of said donations.