## Cover Page
Donation Place
Exported on: 04/01/2020
Generated by: Juan Ruiz
Powered by: Tricentis
Time zone: (GMT -04:00) Eastern Time

## Test Runs_1
DBID | Directory | Id | Name | Status | Test Case Version | Assigned To | Executed Start | Executed End | Planned Start Date | Planned End Date | Logs | Defects | Defect IDs | Test Step # | Test Step Description | Test Step Expected Result | Test Step Actual Result | Test Step Status
60313860 | Iteration-1 / Juan | TR-84 | Update User Profile - Entitlements Testing (Internal, External) | Passed | 3.0 | Juan Ruiz | 03/31/2020 10:51 PM | 03/31/2020 10:51 PM | 03/18/2020 | 03/18/2020 | 1 |  |  | 1 | Test Update User Profile as User | User can access this module. |  | Unexecuted
[14 empty] | 2 | Test Update User Profile as Distribution Manager | Distribution Manager will not have access to this module. |  | Unexecuted
[14 empty] | 3 | Test Update User Profile as Fleet Team Manager | Fleet Team Manager will not have access to the module. |  | Unexecuted
[14 empty] | 4 | Test Update User Profile as Data Analyst | Data Analyst can access this module. |  | Unexecuted
[14 empty] | 5 | Test Update User Profile as Financial Manager | Financial Manager will not have access to this module. |  | Unexecuted
[14 empty] | 6 | Test Update User Profile as Administrator | Administrator can have access to this module. |  | Unexecuted
[14 empty] | 7 | Test Update User Profile as User Support | User Support will not have access to this module. |  | Unexecuted
[14 empty] | 8 | Test Update User Profile as Account Manager | Account Manager can access to this module. |  | Unexecuted
[14 empty] | 9 | Test Update User Profile as Delivery System | Delivery System will not have access to this module. |  | Unexecuted
[14 empty] | 10 | Test Update User Profile as Non Profit Organization | Non Profit Organizations will not have access to this module. |  | Unexecuted
[14 empty] | 11 | Test Update User Profile as Government Agency | Government Agency will not have access to this module. |  | Unexecuted
60313867 | Iteration-1 / Juan | TR-85 | Update User Profile - GUI Features Testing | Passed | 4.0 | Daniel Berekdar | 03/31/2020 10:53 PM | 03/31/2020 10:53 PM | 03/18/2020 | 03/18/2020 | 1 |  |  | 1 | Log In to User Account with User Account information | Login Successful + Authentication with Firebase Database |  | Unexecuted
[14 empty] | 2 | Select User Profile in Bottom Navbar | Profile Screen is displayed. |  | Unexecuted
[14 empty] | 3 | View User Profile in Portrait Mode. | Profile change forms should remain in portrait mode, no distortions or changes. |  | Unexecuted
[14 empty] | 4 | View User Profile in Landscape Mode | User Profile forms should adhere to the previous portrait mode, and remain to scale and undistorted. |  | Unexecuted
[14 empty] | 5 | View User Form Progress | The progress in the form should be visible in real time. |  | Unexecuted
60313813 | Iteration-1 / Juan | TR-75 | Update User Profile - Field Validation Testing | Passed | 2.0 | Javier Teitelbaum | 03/31/2020 10:53 PM | 03/31/2020 10:53 PM | 03/18/2020 | 03/18/2020 | 1 |  |  | 1 | Log In to User Account with User Account information | Login Successful + Authentication with Firebase Database are consistent. |  | Unexecuted
[14 empty] | 2 | Select User Profile in Bottom Navbar | Profile Screen is displayed and is changed in the Firebase Database. |  | Unexecuted
60313762 | Iteration-1 / Juan | TR-68 | Update User Profile - Field Validation Testing (First Name) | Passed | 1.0 | Juel Abreu | 03/31/2020 09:56 PM | 03/31/2020 09:56 PM | 03/18/2020 | 03/18/2020 | 1 |  |  | 1 | Log In to User Account with User Account information | Login Successful + Authentication with Firebase Database are consistent. |  | Unexecuted
[14 empty] | 2 | Select User Profile in Bottom Navbar | Profile Screen is displayed and is changed in the Firebase Database. |  | Unexecuted
[14 empty] | 3 | Change User First Name, adding special characters | First Name is not changed locally and a warning is issued to the user. |  | Unexecuted
[14 empty] | 4 | Change User First Name, leaving blank | First Name is not changed locally and a warning is issued to the user. |  | Unexecuted
[14 empty] | 5 | Change User First Name, putting in more than 20 characters | First Name is not changed locally and a warning is issued to the user. |  | Unexecuted
[14 empty] | 6 | Change User First Name, putting less than 2 characters | First Name is not changed locally and a warning is issued to the user. |  | Unexecuted
60313763 | Iteration-1 / Juan | TR-69 | Update User Profile - Field Validation Testing (Last Name) | Passed | 1.0 | Juel Abreu | 03/31/2020 09:56 PM | 03/31/2020 09:56 PM | 03/18/2020 | 03/18/2020 | 1 |  |  | 1 | Log In to User Account with User Account information | Login Successful + Authentication with Firebase Database are consistent. |  | Unexecuted
[14 empty] | 2 | Select User Profile in Bottom Navbar | Profile Screen is displayed and is changed in the Firebase Database. |  | Unexecuted
[14 empty] | 3 | Change User Last Name, leaving blank | Last Name is not changed locally and a warning is issued to the user. |  | Unexecuted
[14 empty] | 4 | Change User Last Name, adding special characters | Last Name is not changed locally and a warning is issued to the user. |  | Unexecuted
[14 empty] | 5 | Change User Last Name, putting in more than 20 characters | Last Name is not changed locally and a warning is issued to the user. |  | Unexecuted
[14 empty] | 6 | Change User Last Name, putting less than 2 characters | Last Name is not changed locally and a warning is issued to the user. |  | Unexecuted
60313764 | Iteration-1 / Juan | TR-70 | Update User Profile - Field Validation Testing (Street 1 and 2 Address) | Passed | 1.0 | Daniel Berekdar | 03/31/2020 09:56 PM | 03/31/2020 09:56 PM | 03/18/2020 | 03/18/2020 | 1 |  |  | 1 | Log In to User Account with User Account information | Login Successful + Authentication with Firebase Database are consistent. |  | Unexecuted
[14 empty] | 2 | Select User Profile in Bottom Navbar | Profile Screen is displayed and is changed in the Firebase Database. |  | Unexecuted
[14 empty] | 3 | Change User Street 1 and 2 Address, use a fake address. | Street 1 and Street 2 Address is not changed locally and is not changed in the firebase database. A warning is issued to the user. |  | Unexecuted
[14 empty] | 4 | Change User Street 1 and 2 Address, less than two characters | Street 1 and Street 2 Address is not changed locally and is not changed in the firebase database. A warning is issued to the user. |  | Unexecuted
[14 empty] | 5 | Change User Street 1 and 2 Address, left blank | Street 1 and Street 2 Address is not changed locally and is not changed in the firebase database. A warning is issued to the user. |  | Unexecuted
60313769 | Iteration-1 / Juan | TR-71 | Update User Profile - Field Validation Testing (Zip Code) | Passed | 1.0 | Juan Ruiz | 03/31/2020 09:56 PM | 03/31/2020 09:56 PM | 03/18/2020 | 03/18/2020 | 1 |  |  | 1 | Log In to User Account with User Account information | Login Successful + Authentication with Firebase Database are consistent. |  | Unexecuted
[14 empty] | 2 | Select User Profile in Bottom Navbar | Profile Screen is displayed and is changed in the Firebase Database. |  | Unexecuted
[14 empty] | 3 | Change User Zip, leaving blank | Zip Code isn't changed. A warning is issued to the user. |  | Unexecuted
[14 empty] | 4 | Change User Zip, putting in more than 20 characters | Zip Code isn't changed. A warning is issued to the user. |  | Unexecuted
[14 empty] | 5 | Change User Zip, putting less than 6 characters | Zip Code isn't changed. A warning is issued to the user. |  | Unexecuted
[14 empty] | 6 | Change User Zip, putting more than 6 characters | Zip Code isn't changed. A warning is issued to the user. |  | Unexecuted
60313771 | Iteration-1 / Juan | TR-72 | Update User Profile - Field Validation Testing (City) | Passed | 1.0 | Javier Teitelbaum | 03/31/2020 09:57 PM | 03/31/2020 09:57 PM | 03/18/2020 | 03/18/2020 | 1 |  |  | 1 | Log In to User Account with User Account information | Login Successful + Authentication with Firebase Database are consistent. |  | Unexecuted
[14 empty] | 2 | Select User Profile in Bottom Navbar | Profile Screen is displayed and is changed in the Firebase Database. |  | Unexecuted
[14 empty] | 3 | Change User City, leaving blank | City isn't changed. A warning is issued to the user. |  | Unexecuted
[14 empty] | 4 | Change User City, putting in more than 20 characters | City isn't changed. A warning is issued to the user. |  | Unexecuted
[14 empty] | 5 | Change User City, putting less than 6 characters | City isn't changed. A warning is issued to the user. |  | Unexecuted
[14 empty] | 6 | Change User City, putting more than 6 characters | City isn't changed. A warning is issued to the user. |  | Unexecuted
60313823 | Iteration-1 / Juan | TR-76 | Update User Profile - Core Functionality Testing | Passed | 2.0 | Juan Ruiz | 03/31/2020 10:55 PM | 03/31/2020 10:55 PM | 03/18/2020 | 03/18/2020 | 1 |  |  | 1 | Log In to User Account with User Account Information | Login Successful + Authentication with Firebase Database |  | Unexecuted
[14 empty] | 2 | Select User Profile in Bottom Navbar | Profile Screen is displayed. |  | Unexecuted
[14 empty] | 3 | Change User First Name | First Name is updated locally and on Firebase. |  | Unexecuted
[14 empty] | 4 | Change User Last Name | Last Name is updated locally and on Firebase. |  | Unexecuted
[14 empty] | 5 | Change User Street 1 Address | Street 1 Address is changed locally and on Firebase. |  | Unexecuted
[14 empty] | 6 | Change User Street 2 Address | Street 2 Address is changed locally and on Firebase. |  | Unexecuted
[14 empty] | 7 | Change User City | City Address is changed locally and on Firebase. |  | Unexecuted
[14 empty] | 8 | Change User State | State is updated locally and on Firebase. |  | Unexecuted
[14 empty] | 9 | Change User Zip | Zip Code is updated locally and on Firebase. |  | Unexecuted
60313825 | Iteration-1 / Juan | TR-77 | Donation In Honor Of - GUI Features Testing | Passed | 2.0 | Juel Abreu | 03/31/2020 10:56 PM | 03/31/2020 10:56 PM | 03/18/2020 | 03/18/2020 | 1 |  |  | 1 | Navigate to create list tab | Should be able to open create list tab |  | Unexecuted
[14 empty] | 2 | Click on text field | Selected text field should be activated and be able to enter content |  | Unexecuted
[14 empty] | 3 | Enter text in the text field | The text entered should correctly displayed in the text field and not get blocked |  | Unexecuted
60313829 | Iteration-1 / Juan | TR-78 | Donation In Honor Of - Core Functionality Testing | Passed | 1.0 | Daniel Berekdar | 03/31/2020 10:56 PM | 03/31/2020 10:56 PM | 03/18/2020 | 03/18/2020 | 1 |  |  | 1 | Enter donation in honor of in the text field | Donation in honor of should be able to be added |  | Unexecuted
[14 empty] | 2 | Delete donation in honor of from the text field | Would be able to delete the info |  | Unexecuted
[14 empty] | 3 | Enter new donation in honor of name | The name allowed to be re-entered |  | Unexecuted
[14 empty] | 4 | Click the create donation list button | Donation in honor of get stored in local donation list |  | Unexecuted
[14 empty] | 5 | Check Firebase donation in honor of info | Should correct display in Firebase database |  | Unexecuted
60313831 | Iteration-1 / Juan | TR-79 | Donation In Honor Of - Entitlements Testing | Passed | 2.0 | Javier Teitelbaum | 03/31/2020 10:56 PM | 03/31/2020 10:56 PM | 03/18/2020 | 03/18/2020 | 1 |  |  | 1 | Test Donation in Honor of as User | User can access this module. |  | Unexecuted
[14 empty] | 2 | Test Donation in Honor as Distribution Manager | Distribution Manager can access to this module. |  | Unexecuted
[14 empty] | 3 | Test Donation in Honor as Fleet Team Manager | Fleet team manager will not access to the module. |  | Unexecuted
[14 empty] | 4 | Test Donation in Honor as Data Analyst | Data Analyst will not have access to this module. |  | Unexecuted
[14 empty] | 5 | Test Donation in Honor as Financial Manager | Financial Manager will not have access to this module. |  | Unexecuted
[14 empty] | 6 | Test Donation in Honor as Administrator | Administrator will not have access to this module. |  | Unexecuted
[14 empty] | 7 | Test Donation in Honor as User Support | User Support can access to this module. |  | Unexecuted
[14 empty] | 8 | Test Donation in Honor as Account Manager | Account Manager will not have access to this module. |  | Unexecuted
[14 empty] | 9 | Test Donation in Honor as Delivery System | Delivery System will not have access to this module. |  | Unexecuted
[14 empty] | 10 | Test Donation in Honor as Non Profit Organization | Non Profit Organizations will not have access to this module. |  | Unexecuted
[14 empty] | 11 | Test Donation in Honor as Government Agency | Government Agency will not have access to this module |  | Unexecuted
60313835 | Iteration-1 / Juan | TR-80 | Create Donation List - GUI Features Testing | Failed | 2.0 | Daniel Berekdar | 03/31/2020 10:45 PM | 03/31/2020 10:45 PM | 03/18/2020 | 03/18/2020 | 1 | 1 | DF-11 | 1 | Navigate to the create donation list tab | Be able to view the create donation list page displayed correctly |  | Unexecuted
[14 empty] | 2 | Check the display of item field | The item field should be able to be displayed |  | Unexecuted
[14 empty] | 3 | Look at each text field | The hint text should be displayed |  | Unexecuted
60313838 | Iteration-1 / Juan | TR-81 | Create Donation List - Core Functionality Testing | Passed | 2.0 | Juan Ruiz | 03/31/2020 10:56 PM | 03/31/2020 10:56 PM | 03/18/2020 | 03/18/2020 | 1 |  |  | 1 | Click on create donation list tab | Create donation list tab could be opened by click |  | Unexecuted
[14 empty] | 2 | Enter number in the item field | Number should be allowed to entered |  | Unexecuted
[14 empty] | 3 | Delete number in the item field | Number should be allowed to deleted |  | Unexecuted
[14 empty] | 4 | Click add button | A form should printed out in terminal with according number and firebase should have the list created |  | Unexecuted
60313841 | Iteration-1 / Juan | TR-82 | Create Donation List - Field Edit Validation | Failed | 2.0 | Javier Teitelbaum | 03/31/2020 10:46 PM | 03/31/2020 10:46 PM | 03/18/2020 | 03/18/2020 | 1 | 1 | DF-10 | 1 | Try to Enter Number in the item field | Numbers should be allowed in the item fields |  | Unexecuted
[14 empty] | 2 | Enter item name in the item field | The item name should not be allowed to get entered |  | Unexecuted
[14 empty] | 3 | Left unwanted field blank | List should still be allowed to be generated |  | Unexecuted
[14 empty] | 4 | Check the number generated for blank field | The number should be 0 |  | Unexecuted
60313844 | Iteration-1 / Juan | TR-83 | Create Donation List - Entitlements Testing | Passed | 2.0 | Juan Ruiz | 03/31/2020 10:56 PM | 03/31/2020 10:56 PM | 03/18/2020 | 03/18/2020 | 1 |  |  | 1 | Test Create Donation List as User | User can access this module. |  | Unexecuted
[14 empty] | 2 | Test Create Donation List as Distribution Manager | Distribution Manager will not have access to this module. |  | Unexecuted
[14 empty] | 3 | Test Create Donation List as Fleet Team Manager | Fleet team manager will not have access to the module. |  | Unexecuted
[14 empty] | 4 | Test Create Donation List as Data Analyst | Data Analyst can access to this module. |  | Unexecuted
[14 empty] | 5 | Test Create Donation List as Financial Manager | Financial Manager will not have access to this module |  | Unexecuted
[14 empty] | 6 | Test Create Donation List as Administrator | Administrator will not have access to this module. |  | Unexecuted
[14 empty] | 7 | Test Create Donation List as User Support | User Support can access to this module. |  | Unexecuted
[14 empty] | 8 | Test Create Donation List as Account Manager | Account Manager will not have access to this module. |  | Unexecuted
[14 empty] | 9 | Test Create Donation List as Delivery System | Delivery System will not have access to this module. |  | Unexecuted
[14 empty] | 10 | Test Create Donation List as Non Profit Organization | Non Profit Organizations can access to this module |  | Unexecuted
[14 empty] | 11 | Test Create Donation Lists Government Agency | Government Agency will not have access to this module. |  | Unexecuted